## Register
SRMAM Risk Register Template
Serial | Source | Nature of Risk | Risk Family | The Risk What can happen and how it can happen | Inherent Likelihood (1 low to 6 high) | Potential Consequence (1 low to 6 high) | Risk Score | Inherent Risk Rating | Existing Controls Rating | Effectiveness of Existing Controls | Residual Likelihood (1 low to 6 high) | Residual (Probable) Consequence (1 low to 6 high) | Risk Score | Current Risk Rating | Risk Priority
1 | Commercial and legal relationships | Unsustainable in terms of our cost performance | Financial | Failure to manage within budget or deliver portfolio outcomes within budget through poor financial management | 5 Likely | reputation, financial, community, | #VALUE! | #VALUE! | 2 | Somewhat Inadequate | 5 Likely | 4 Major | 4 | Extreme | 1
2 | Commercial and legal relationships | Failure to deliver Capital Projects. | Financial | Degradation of opportunity value through poor execution of Projects due to a lack of capability and or understanding of operating environment | 5 Likely | Financial, reputation, delays, Portfolio outcomes, community | #VALUE! | #VALUE! | 2 | Somewhat Inadequate | 6 Very Likely | 3 Moderate | 4 | Extreme | 1
3 | Management activities and controls | Future Capability Gap. | Human | Failure to deliver on portfolio outcomes due to insufficient capability (including contractors) in key areas | 6 Very Likely | Portfolio outcomes, financial, delays, community | #VALUE! | #VALUE! | 2 | Somewhat Inadequate | 6 Very Likely | 4 Major | 3 | Extreme | 1
4 | Management activities and controls | Knowledge & Information Management | Human | Information not accessible to the organisation and knowledge being lost as a result | 5 Likely | Portfolio outcomes, financial, delays | #VALUE! | #VALUE! | 3 | Mostly Adequate | 4 Possible | 3 Moderate | 6 | High | 2
5 | Management activities and controls | Current Capability Gap | Human | Inability to deliver on today's objectives efficiently | 5 Likely | Financial, reputation, delays | #VALUE! | #VALUE! | 3 | Mostly Adequate | 4 Possible | 4 Major | 5 | High | 2
6 | Technology and technical issues | Technology Plan | Technological | Failure to meet expectations and/or business needs | 4 Possible | Reputation, Financial | #VALUE! | #VALUE! | 3 | Mostly Adequate | 5 Likely | 2 Minor | 6 | High | 2
7 | Individual activities | Security | Security | Failure to meet safety and security standards with resultant loss of security control, leading to injury, financial loss, reputation damage etc due to internal or external threat (theft, fraud, information breach, terrorist attack, etc) | 5 Likely | Financial, human, information, reputation, Privacy | #VALUE! | #VALUE! | 3 | Mostly Adequate | 5 Likely | 3 Moderate | 5 | High | 2
8 | Human behaviour | Occupational Health Issues | Occupational health and safety | Slips, trips, falls, manual handling, harrassment, stress related injuries, etc. | 5 Likely | Injury, financial loss, morale | #VALUE! | #VALUE! | 3 | Mostly Adequate | 4 Possible | 2 Minor | 7 | Medium | 3
9 | Management activities and controls | Inappropriate Business Strategy | Human | Failure to understand or respond to Minister's/Government/ community requirements | 4 Possible | Reputation, community, financial | #VALUE! | #VALUE! | 5 | Exceeds Req'ts | 3 Unlikely | 2 Minor | 8 | Medium | 3
10 | Political circumstances | Loss of Government Support | Economic | Loss of funding etc. due to loss of political support/confidence | 4 Possible | Reputation, portfolio outcomes, community, financial | #VALUE! | #VALUE! | 4 | Appropriate | 1 Remote | 5 Massive | 7 | Medium | 3
11 | Management activities and controls | Crisis Management. | Environmental | Managing a crisis badly (Eg: SARS, Avian Flu, etc) | 5 Likely | Reputation, community, financial | #VALUE! | #VALUE! | 4 | Appropriate | 3 Unlikely | 3 Moderate | 7 | Medium | 3
12 | Human behaviour | Industrial Relations. | Human | Failure to manage employee relations and/or external relations (eg: union) | 4 Possible | Delays, financial, portfolio outcomes, reputation | #VALUE! | #VALUE! | 4 | Appropriate | 3 Unlikely | 3 Moderate | 7 | Medium | 3
13 | Management activities and controls | Contractor Management | Human | Lack of appropriate control over contractors | 5 Likely | Delays, financial | #VALUE! | #VALUE! | 4 | Appropriate | 4 Possible | 2 Minor | 7 | Medium | 3
14 | Technology and technical issues | Catastrophic key facility failure | Technological | Loss of access to essential infrastructure and/or buildings (Eg: Crisis management room) leads to business continuity interruption | 3 Unlikely | Reputation, financial, resource base, | #VALUE! | #VALUE! | 3 | Mostly Adequate | 2 Highly Unlikely | 1 Slight | 10 | Low | 4
15 | Technology and technical issues | 3rd Party Infrastructure Failure. | Technological | Failure of external critical infrastructure (Eg: telecommunications, Internet connectivity, water, electricity). Lack of knowledge of 3rd party risk management plans | 4 Possible | Reputation, financial | #VALUE! | #VALUE! | 4 | Appropriate | 2 Highly Unlikely | 2 Minor | 9 | Low | 4
Source: Security Risk Management Aide-Mémoire
www.srmam.com
| Commercial and legal relationships |  |  | Diseases
| Economic circumstances |  |  | Economic
| Human behaviour |  |  | Environmental
| Natural events |  |  | Financial
| Political circumstances |  |  | Human
| Technology and technical issues |  |  | Natural hazards
| Management activities and controls |  |  | Occupational health and safety
| Individual activities |  |  | Product liability
Professional liability
Property damage
Public liability
Security
Technological
Note on F2: Consider the hazard/risk identified….. What is the likelihood of this type of consequence occurring in the next twelve months. 1 Remote 2 Highly Unlikely 3 Unlikely 4 Possible 5 Likely 6 Very Likely Enter the corresponding probability rating (1-6) into this column.
Note on G2: Consider the hazards/risk identified.... The consequence of the event occurring needs to be considered as per categories on Risk Matrix. 1 Slight 2 Minor 3 Moderate 4 Major 5 Massive 6 Catastrophic
Note on J2: Consider the barriers and controls which are in place to prevent or mitigate this risk, the quality of implementation and their operational effectiveness. 1 Inadequate 2 Inadequate in some areas or circumstances 3 Adequate in most conditions 4 Adequate in current conditions with appropriate cost/benefit balance. 5 Exceeds requirements - could potentially save money/resourcs without reducing effectiveness.
Note on L2: Consider the hazard/risk identified….. What is the likelihood of this type of consequence occurring in the next twelve months. 1 Remote 2 Highly Unlikely 3 Unlikely 4 Possible 5 Likely 6 Very Likely Enter the corresponding probability rating (1-6) into this column.
Note on M2: Consider the hazards/risk identified.... The consequence of the event occurring needs to be considered as per categories on Risk Matrix. 1 Slight 2 Minor 3 Moderate 4 Major 5 Massive 6 Catastrophic
Sort by Treatment Priority
Sort by Risk Rating
Numerical Order
Sort by Risk Rating

## Treatment_Plan
Security Risk Treatment Plan Template
Serial | Ref: Section of SRA | Treatment Recommendation | Main Risk Treated (Serial from Risk Reg.) | Main Risk Treated (Desc. from Risk Reg.) | Priority from Risk Register | Estimated Cost of Control | A: Accept R: Reject | Person Responsible | Due Date | How will this item be monitored & treatment options completed
1 | General | Project Management Team to manage and monitor the implementation and re-sourcing of the Risk Treatment Plan. | 28 | Environmental | 3 Unlikely | Internal Labour |  | F Nerks |  | Minutes of Project Team meetings tabled for Executive Management team review
2 | General | Identify one individual as Project Manager who is responsible for implementation of the Risk Treatment Plan, preferably as a full time fixed term position. | 28 | Environmental | 3 Unlikely | 100000 |  | F Nerks |  | Creation of Job Description and recruitment of individual. Progress monitored through weekly reports to Supervisor.
3 | General | Develop a comprehensive Communications Plan for use prior to and during implementation. | 28 | Environmental | 3 Unlikely | Internal Labour |  | F Nerks |  | Communications Plan signed off by Management Team
4 | Access Control | Review signage, adopting a consistent message regarding access / egress. | 27 | Environmental | 3 Unlikely | Internal Labour |  | F Nerks |  | Report signed off by Management Team.
5 | Access Control | Adopt risk management approach with a view to the identification of high, medium & low risk areas, that require / necessitate active access / egress management. | 8 | Occupational health and safety | 4 Possible | Internal Labour |  | F Nerks
6 | Access Control | Identify a range of access / egress options to be applied, reflective of identified and adopted criteria for installation of the same, including: - Mechanical key pads, Electronic key pads, Biometric key entry (Iris & Fingerprint), Electric key card entry / egress, Security proximity card | 8 | Occupational health and safety | 4 Possible | 25000 |  | F Nerks
7 | Access Control | Implement associated audit(s) trails pertaining to: - System status and verification, Access level(s), User groups, Operator privilege(s) | 25 | Environmental | 3 Unlikely | Internal Labour |  | F Nerks
8 | Access Control | Implement generic Security platform across all <Organization> sites.` | 28 | Environmental | 3 Unlikely | 420000 |  | F Nerks
9 | Theft | Conduct an assessment of the cost of annual thefts to assess the priority. | 24 | Environmental | 3 Unlikely | 15000 |  | F Nerks
10 | Theft | Existing security measures be implemented more effectively (Eg: Searches, Auditing of Material Gate Passes, Permanent marking of assets etc). | 24 | Environmental | 3 Unlikely | 0 |  | F Nerks
11 | Theft | Implement a regular system audit to monitor the effectiveness of EH Access Control Procedures. | 21 | Environmental | 3 Unlikely | Internal Labour |  | F Nerks
12 | Theft | Develop an introductory level asset management and security awareness program for line managers | 24 | Environmental | 3 Unlikely |  |  | F Nerks
13 | Alarms | Adopt a consistent and criteria based approach to: alarm application, reflective of security risk assessments, subsequent risk identification and recommended treatment profile, Alarm selection (hardware), installation, monitoring and response procedure(s) | 8 | Occupational health and safety | 4 Possible |  |  | F Nerks
14 | Security Awareness | Basic security awareness training for all personnel, as part of the induction process, and via Global e-mails, EH Newsletter, Toolbox meetings etc. | 8 | Occupational health and safety | 4 Possible |  |  | F Nerks
15 | Security Awareness | Bomb Threat training for Fire Wardens | 13 | Environmental | 3 Unlikely |  |  | F Nerks
16 | Security Awareness | Implement an electronic register for recording and categorising security incidents to conduct analysis and trend reporting. | 8 | Occupational health and safety | 4 Possible |  |  | F Nerks
17 | Security Personnel | Tender for one Security manpower contract for all sites. | 28 | Environmental | 3 Unlikely |  |  | F Nerks
18 | Doors & Windows | Area stakeholders to carry out and document monthly inspections of the condition of doors and windows and report to Maintenance dept. | 24 | Environmental | 3 Unlikely |  |  | F Nerks
19 | Doors & Windows | Security Officers to record observations as a routine element of their regular security patrols | 24 | Environmental | 3 Unlikely |  |  | F Nerks
20 | Documentation | Prepare detailed security instructions for all departments in accordance with AS 4485 by a professional security risk manager. | 28 | Environmental | 3 Unlikely |  |  | F Nerks
21 | Documentation | Promulgate benchmarked and health-specific security instructions for the application of security services across <Organization> | 28 | Environmental | 3 Unlikely |  |  | F Nerks
22 | Documentation | Prepare detailed Critical Path Analysis and Action Plan to project manage the implementation of Security instructions. | 28 | Environmental | 3 Unlikely |  |  | F Nerks
23 | Documentation | Implement a 'Clean Desk' policy at EH whereby all classified information is securely locked away on completion of each day's work or when the work area is left unattended for an extended period. | 25 | Environmental | 3 Unlikely |  |  | F Nerks
24 | Documentation | Provide staff with facilities to secure their sensitive documents each night (Eg. Lockable desk drawers or roll down document lockers). | 25 | Environmental | 3 Unlikely |  |  | F Nerks
25 | Documentation | Raise awareness about the availability of e-mail encryption and general Information Security guidelines through inclusion in the Induction Process. | 25 | Environmental | 3 Unlikely |  |  | F Nerks
26 | Documentation | Implement annual workgroup level Security Inspections utilising the Office Information Security Inspection Check List | 25 | Environmental | 3 Unlikely |  |  | F Nerks
27 | Training | <Organization> incorporates aggression management and associated security briefings into their weekly monthly and annual training regimes. | 8 | Occupational health and safety | 4 Possible |  |  | F Nerks
28 | Training | Target specific funding to enable the training programs to be initiated and maintained. | 8 | Occupational health and safety | 4 Possible |  |  | F Nerks
29 | Training | Introduce security briefing(s) into the <Organization> 'General Induction' for staff. | 8 | Occupational health and safety | 4 Possible |  |  | F Nerks
30 | Training | Introduce security briefings (department specific briefings) raising security awareness and the specific issues pertinent to individual department(s) | 8 | Occupational health and safety | 4 Possible |  |  | F Nerks
31 | General | Redefine the security organisational chart within the broader <Organization> organisational chart, clearly identifying / defining reporting lines, responsibilities and function(s). | 28 | Environmental | 3 Unlikely |  |  | F Nerks
32 | General | Draft a security department brief and scope, including objectives, associated tasks and responsibilities of the same. | 28 | Environmental | 3 Unlikely |  |  | F Nerks
33 | General | Employ professional security risk manager who can project manage all approved aspects of the Treatment Plan | 28 | Environmental | 3 Unlikely |  |  | F Nerks
34 | Hazardous Material | Implement locked door and locked storage container procedures to be used 24 hour per day at all locations having radioactive isotopes or toxic chemicals such as film developer, cleaning products etc. | 26 | Environmental | 3 Unlikely |  |  | F Nerks
35 | Hazardous Material | Biological Waste Containers should be stored in locked compounds or other areas with limitations on the access to those designated as authorised persons. Additionally, signage warning of the risk of entry should be prominently displayed. | 26 | Environmental | 3 Unlikely |  |  | F Nerks
36 | Incident Reporting | The incident recording and analysis program is scoped, planned and implemented to run alongside the general improvement program. | 8 | Occupational health and safety | 4 Possible |  |  | F Nerks
37 | Information Systems | Conduct initial review and rectification then implement quarterly reports to workgroup supervisors as to who has access to their File shares to ensure that personnel who carry user access privileges from one position to the next can be identified and appropriate action taken. | 4 | Human | 4 Possible |  |  | F Nerks
38 | Information Systems | Review data backup storage processes to ensure that backups are stored in a physically remote location (from the server room) with adequate levels of fire and physical security protection in accordance with <Organization> standards. | 3 | Human | 6 Very Likely |  |  | F Nerks
39 | Information Systems | Conduct a network penetration test and review of network topology to identify potential weaknesses and options to ensure that Process Control and Security Systems are adequately protected. | 6 | Technological | 5 Likely |  |  | F Nerks
40 | Information Systems | Upgrade detection and suppression systems in all server and communications rooms. | 12 | Environmental | 3 Unlikely |  |  | F Nerks
41 | Information Systems | Implement a Disaster Recovery Plan for critical assets and data | 12 | Environmental | 3 Unlikely |  |  | F Nerks
42 | keys & Locks | Modify Security Instructions to ensure quarterly key audits. | 28 | Environmental | 3 Unlikely |  |  | F Nerks
43 | keys & Locks | Write Key Security Handling in accordance with the guidelines in <Standard/Policy>. | 28 | Environmental | 3 Unlikely |  |  | F Nerks
44 | keys & Locks | Ensure that key security receives close attention during the period of security enhancement and redress the key problems by ensuring correct handling in the future. | 24 | Environmental | 3 Unlikely |  |  | F Nerks
45 | Lighting | That individual stakeholders and security officers on patrol observe and report any issues with internal and external lighting, for the attention of the Engineering Department. | 8 | Occupational health and safety | 4 Possible |  |  | F Nerks
46 | Lighting | Formalise criteria for lighting to maintain an effective internal and external protective security and safety lighting system as detailed in the report. | 8 | Occupational health and safety | 4 Possible |  |  | F Nerks
47 | Monitoring | This security risk assessment and associated risk management strategies should be reviewed either annually, when a major incident occurs or at any time that a manifest change occurs to the health industry, <Organization> or the threat environment. | 28 | Environmental | 3 Unlikely |  |  | F Nerks
48 | Monitoring | Review should follow on and develop the methodologies outlined in the SRA and should be conducted at all levels including Assets; Procedures; Workgroups; and Individuals | 28 | Environmental | 3 Unlikely |  |  | F Nerks
49 | New Buildings | Recommended <Organization> establish a set of criteria to enable correlation of risks and profiles against building design(s), reflective of a range of likely risk profiles (within identified service areas, with a view to establishing a consistent approach to security infrastructure). | 8 | Occupational health and safety | 4 Possible |  |  | F Nerks
50 | New Buildings | Security Risk Analyst(s) be consulted during project briefings and design, where aforementioned criteria and operational context would be considered, when determining appropriate security equipment and associated infrastructure. | 28 | Environmental | 3 Unlikely |  |  | F Nerks
51 | New Buildings | Defence in Depth and CPTED principles be adopted in evaluation and decision making processes | 28 | Environmental | 3 Unlikely |  |  | F Nerks
52 | Newborn | It is recommended that all Newborn areas of EH develop a formal written security policy based on specific local requirements, but predicated on the excellent guidelines in Section 13 (Newborn and Paediatric Security) contained within AS 4485. | 28 | Environmental | 3 Unlikely |  |  | F Nerks
53 | Newborn | Include Policy review for <specific> areas in the portfolio of a professional security and risk manager. | 28 | Environmental | 3 Unlikely |  |  | F Nerks
54 | Physical Security | Review the current preventative maintenance program for perimeter fencing and lighting | 8 | Occupational health and safety | 4 Possible |  |  | F Nerks
55 | Physical Security | Fix trespass-warning signs to restricted areas (such that at least two would be visible from any direction of approach). | 27 | Environmental | 3 Unlikely |  |  | F Nerks
56 | Physical Security | It is recommended that a study be conducted to integrate all swipe card, access control, CCTV and Photo ID card imaging onto one centralised platform operating across all sites. | 28 | Environmental | 3 Unlikely |  |  | F Nerks
57 | Custodial | <Organization> to initiate consultation / discussion with Police Command via <Organization> Security Representative; regarding retention of Police manpower resources within <specific> Departments when <client> status has been established / identified. | 7 | Security | 5 Likely |  |  | F Nerks
58 | Custodial | Further consultation be initiated by <Organization> Security Representative, with a view to identifying need, preferred location, design specifications, consideration of 'gazetting' to enable persons to be managed while in distress. | 7 | Security | 5 Likely |  |  | F Nerks
59 | Custodial | Interim measures to be established ensuring that identified individuals are where practicable, located in a relatively isolated and suitably designed area within the <specific> Department. (Free of potential weapons, alternate escape route for staff). | 7 | Security | 5 Likely |  |  | F Nerks
60 | Custodial | Establish protocols for attending staff / personnel, with a view to personal safety. | 7 | Security | 5 Likely |  |  | F Nerks
61 | Recruitment | Review HR recruitment procedures to include psychological and/or criminal assessment pre-employment. | 16 | Environmental | 3 Unlikely |  |  | F Nerks
62 | Recruitment | Assess and review formal systems for ongoing regular appraisal of employees psychological/stress profiles | 16 | Environmental | 3 Unlikely |  |  | F Nerks
63 | Fire Systems | Secure and occlude from view all critical fire fighting systems such as pumps, valves and distribution points in all facilities. | 12 | Environmental | 3 Unlikely |  |  | F Nerks
64 | Personnel | Security program to be linked to the security risk mitigation program at EH and be driven by top management and supported actively by all management and staff. | 8 | Occupational health and safety | 4 Possible |  |  | F Nerks |  | Visible management support. Eg: Allocation of resources, training, presentations by management, etc.
65 | Signage | Procedures be modified such that all stakeholders and patrolling security officers carry out an ongoing review of signage in their areas with a view to replacing or installing. | 27 | Environmental | 3 Unlikely |  |  | F Nerks
66 | Surveillance Systems | CCTV systems to be reviewed across key <Organization> site(s), in view of this report. | 8 | Occupational health and safety | 4 Possible |  |  | F Nerks
67 | Surveillance Systems | CCTV Profile and recommended locations of cameras be predicated upon recommendations arising from this report…i.e. identified high-risk area(s). | 8 | Occupational health and safety | 4 Possible |  |  | F Nerks
Source: Security Risk Management Aide-Mémoire
www.srmam.com
Sort by Priority
Numerical Order
Note on C3: Details of Recommendation -ACTIONABLE: What do we need to do? -ACHIEVABLE: How will we know when it is completed? -APPROPRIATE: Does it fix the problem? -AGREED: Does the Stakeholder agree to implement it?
Note on D3: Which particular risk(s) does it address?
Note on E3: Which particular risk(s) does it address?
Note on H3: Decision by Stakeholder after evaluation of cost etc.

## Risk Matrix
CORPORATE RISK MATRIX | [7 empty] | LIKELIHOOD
[7 empty] | Historical: | "Unheard of in the industry" | "Has occurred once or twice in the industry" | Has occurred many times in the industry, but not in the Organisation | Has occurred once or twice in the Organisation | Has occurred frequently in the Organisation | Has occurred frequently at the location
[7 empty] | Frequency: (Continuous Operation) | Once every 10,000-100,000* years at location | Once every 1,000-10,000 years at location | Once every 100-1,000 years at location | Once every 10-100 years at location | Once every 1-10 years at location | More than once a year at location or continuously
[7 empty] | Probability: (Single activity) | 1 in 100,000-1,000,000* | 1 in 10,000-100,000 | 1 in 1,000-10,000 | 1 in 100-1,000 | 1 in 10-100 | >1 in 10
[8 empty] | 1 | 2 | 3 | 4 | 5 | 6
| People | Environment | Value | Reputation |  |  |  | Remote | Highly Unlikely | Unlikely | Possible | Likely | Highly Likely
CONSEQUENCE | >20 Fatalities (or Permanent Total Disabilities) | Regional scale (>100 km2) Long term/permanent impact | >Value of the organisation and/or >A$1000M | International concern. Major ventures terminated. Company at stake. | A | 6 | Catastrophic
| 4-20 Fatalities (or Permanent Total Disabilities) | Large scale (10-100 km2) Long term (decades) impact | A$100M-A$1000M | Persistent national concern. Long term 'brand' impact. Major venture/asset operations severely restricted. | B | 5 | Massive
| 1-3 Fatalities (or Permanent Total Disabilities) | Medium scale (1-10 km2) Medium term (years) impact | A$10M- A$100M | Medium term national concern. Minor venture or minor asset operations restricted or curtailed. | C | 4 | Major
| Major Injury/illness, Permanent Partial Disability or Lost Work Case >4days | Medium scale (1-10 km2) Short term (months) impact | A$1M- A$10M | National bad mention. Short term regional concern. Close scrutiny of Asset level operations/future proposals. | D | 3 | Moderate
| Minor Injury/illness. Restricted Work Case or Lost Work Case <4 days. | Localised (<1 km2) Short term (weeks) impact | A$100k- A$1M | Short term local concern. Some impact on asset level non-production activities. | E | 2 | Minor
| Slight Injury/illness. First Aid or Medical Treatment Case | Localised (Immediate area) Temporary impact (days) | <A$100k | Local mention only. Quickly forgotten. Freedom to operate unaffected. | F | 1 | Slight
| For more detailed definition of consequences, refer to the appropriate detailed methodologies. | [5 empty] | *Incidents with a frequency of less than once every 100,000 years (continuous operation) or a probability of less than 1E-6 (single activity) can reasonably be screened out on the basis of low likelihood.
Source: Security Risk Management Aide-Mémoire
www.srmam.com
EXTREME
LOW
MEDIUM
HIGH

## Adequacy
Risk Treatment Priorities
ADEQUACY OF EXISTING CONTROLS
|  |  |  | Inadequate | Somewhat Inadequate | Mostly Adequate | Appropriate | Exceeds
|  |  |  | 1 | 2 | 3 | 4 | 5
RISK | S | Severe | 1 | EXTREME | EXTREME | HIGH | HIGH | MEDIUM
| H | High | 2 | EXTREME | HIGH | HIGH | MEDIUM | MEDIUM
| M | Medium | 3 | HIGH | HIGH | MEDIUM | MEDIUM | LOW
| L | Low | 4 | HIGH | MEDIUM | MEDIUM | LOW | LOW
Risk rating is assessed as per SERT Corporate Risk Matrix
Adequacy score is based on qualitative assessment of existing controls as per Bow Tie Table.
1 | Inadequate
2 | Inadequate in some areas or circumstances
3 | Adequate in most conditions
4 | Adequate in current conditions with appropriate cost/benefit balance.
5 | Exceeds current requirements
1 Inadequate
2 Inadequate in some areas or circumstances
3 Adequate in most conditions
4 Adequate in current conditions with appropriate cost/benefit balance.
5 Exceeds current requirements
Source: Security Risk Management Aide-Mémoire
www.srmam.com

## Barriers
Security Related Procedures and Controls
Serial | Document Name | Doc Number | Last Revised | Custodian | Barriers
1 | Access Control Policy |  |  |  | 1 Access Control Policy
2 | Access Control Procedure |  |  |  | 2 Access Control Procedure
3 | Action Tracking System for Audit Process |  |  |  | 3 Action Tracking System for Audit Process
4 | Asbestos and synthetic Mineral Fibre handling |  |  |  | 4 Asbestos and synthetic Mineral Fibre handling
5 | Asbestos Register |  |  |  | 5 Asbestos Register
6 | Audit Procedures |  |  |  | 6 Audit Procedures
7 | Authorised signatories (Authority Levels) |  |  |  | 7 Authorised signatories (Authority Levels)
8 | Bomb Threat Procedure |  |  |  | 8 Bomb Threat Procedure
9 | Budget process |  |  |  | 9 Budget process
10 | Business Risk Management |  |  |  | 10 Business Risk Management
11 | Communications Media Policy |  |  |  | 11 Communications Media Policy
12 | Construction Project Management Procedure |  |  |  | 12 Construction Project Management Procedure
13 | Contractor Management Systems |  |  |  | 13 Contractor Management Systems
14 | Critical task Identification and analysis |  |  |  | 14 Critical task Identification and analysis
15 | Document control |  |  |  | 15 Document control
16 | Group Facilities Annual Audit Plan |  |  |  | 16 Group Facilities Annual Audit Plan
17 | Group Facilities Management Manual |  |  |  | 17 Group Facilities Management Manual
18 | Waste disposal procedure |  |  |  | 18 Waste disposal procedure
19 | Emergency Response training matrix |  |  |  | 19 Emergency Response training matrix
20 | Emergency Response. |  |  |  | 20 Emergency Response.
21 | Engineering Standards Manual. |  |  |  | 21 Engineering Standards Manual.
22 | Environmental Reporting |  |  |  | 22 Environmental Reporting
23 | Fire Plans |  |  |  | 23 Fire Plans
24 | Fitness for Work Program |  |  |  | 24 Fitness for Work Program
25 | Hazardous area classification |  |  |  | 25 Hazardous area classification
26 | HAZMAT, Workplace registers |  |  |  | 26 HAZMAT, Workplace registers
27 | Health management program, incl. Promotion. |  |  |  | 27 Health management program, incl. Promotion.
28 | Hearing conservation program. |  |  |  | 28 Hearing conservation program.
29 | HR policies manual |  |  |  | 29 HR policies manual
30 | HSE Hazards Register |  |  |  | 30 HSE Hazards Register
31 | HSE plan |  |  |  | 31 HSE plan
32 | HSE Training Procedure |  |  |  | 32 HSE Training Procedure
33 | HSERQ Strategic Direction |  |  |  | 33 HSERQ Strategic Direction
34 | Incident Reporting Procedure |  |  |  | 34 Incident Reporting Procedure
35 | Incident Reporting Procedure |  |  |  | 35 Incident Reporting Procedure
36 | Induction Procedure & Systems |  |  |  | 36 Induction Procedure & Systems
37 | Industrial Regulation & management systems |  |  |  | 37 Industrial Regulation & management systems
38 | Information Policy |  |  |  | 38 Information Policy
39 | Information Security Policy |  |  |  | 39 Information Security Policy
40 | IT Management System |  |  |  | 40 IT Management System
41 | Job Hazard Analysis Methodology |  |  |  | 41 Job Hazard Analysis Methodology
42 | Laboratory: Quality Manual Technical lab. |  |  |  | 42 Laboratory: Quality Manual Technical lab.
43 | Lifting & Manual Handling Standards |  |  |  | 43 Lifting & Manual Handling Standards
44 | Maintenance manual |  |  |  | 44 Maintenance manual
45 | Maintenance philosophies, |  |  |  | 45 Maintenance philosophies,
46 | Maintenance planning process |  |  |  | 46 Maintenance planning process
47 | Management Policy Manual |  |  |  | 47 Management Policy Manual
48 | Manual Handling procedure |  |  |  | 48 Manual Handling procedure
49 | Noise survey/tests |  |  |  | 49 Noise survey/tests
50 | OHS Management System |  |  |  | 50 OHS Management System
51 | OHS Manual |  |  |  | 51 OHS Manual
52 | Operating Guidelines and control instructions |  |  |  | 52 Operating Guidelines and control instructions
53 | Patient Information Management |  |  |  | 53 Patient Information Management
54 | Planned meetings (HSE) |  |  |  | 54 Planned meetings (HSE)
55 | Procurement Procedures Manual |  |  |  | 55 Procurement Procedures Manual
56 | Project Management Procedures |  |  |  | 56 Project Management Procedures
57 | Radioactive materials, ionising radiation. |  |  |  | 57 Radioactive materials, ionising radiation.
58 | Records Information management |  |  |  | 58 Records Information management
59 | Recruitment process manual |  |  |  | 59 Recruitment process manual
60 | Restraint Protocols |  |  |  | 60 Restraint Protocols
61 | SAFE Project |  |  |  | 61 SAFE Project
62 | Safety and Health Rep. guide. |  |  |  | 62 Safety and Health Rep. guide.
63 | Security Instructions |  |  |  | 63 Security Instructions
64 | Security Policy |  |  |  | 64 Security Policy
65 | Security Procedure |  |  |  | 65 Security Procedure
66 | Security Risk Assessment |  |  |  | 66 Security Risk Assessment
67 | Security Standards |  |  |  | 67 Security Standards
68 | Staff Training Manual |  |  |  | 68 Staff Training Manual
69 | Supply Chain – Procurement and Logistics |  |  |  | 69 Supply Chain – Procurement and Logistics
70 | Systems administration procedures |  |  |  | 70 Systems administration procedures
71 |  |  |  |  | 71
72 |  |  |  |  | 72
73 |  |  |  |  | 73
74 |  |  |  |  | 74
75 |  |  |  |  | 75
76 |  |  |  |  | 76
77 |  |  |  |  | 77
78 |  |  |  |  | 78
79 |  |  |  |  | 79
80 |  |  |  |  | 80
81 |  |  |  |  | 81
82 |  |  |  |  | 82
83 |  |  |  |  | 83
84 |  |  |  |  | 84
85 |  |  |  |  | 85
86 |  |  |  |  | 86
87 |  |  |  |  | 87
88 |  |  |  |  | 88
89 |  |  |  |  | 89
90 |  |  |  |  | 90
91 |  |  |  |  | 91
92 |  |  |  |  | 92
93 |  |  |  |  | 93
94 |  |  |  |  | 94
95 |  |  |  |  | 95
96 |  |  |  |  | 96
97 |  |  |  |  | 97
98 |  |  |  |  | 98
99 |  |  |  |  | 99
100 |  |  |  |  | 100
101 |  |  |  |  | 101
102 |  |  |  |  | 102
Source: Security Risk Management Aide-Mémoire
www.srmam.com

## Risk Calculator
|  | Consequence Score | Category | Description
|  | 6 | Catastrophic | >$1,000M Loss, >20 deaths, loss of building, irreversible damage to environment | [5 empty] | 6 Catastrophic
|  | 5 | Massive | >$100M loss, >4 death, loss of plant, significant damage to building, long term environment damage, prosecution. | [5 empty] | 5 Massive
|  | 4 | Major | >$10M loss, 1-4 death or permanent disablility significant damage, reportable spill (EPA), regulatory compliance order | [5 empty] | 4 Major
|  | 3 | Moderate | >$1M loss, Major Injury/illness, plant damage, spill requiring emergency services, regulatory notice | [5 empty] | 3 Moderate
|  | 2 | Minor | >$100K loss, Minor injury or LTI, minor plant damage, local spill, | [5 empty] | 2 Minor
|  | 1 | Slight | <$100K loss, first aid, minor plant damage, local spill, | [5 empty] | 1 Slight
|  | Probability | Description
|  | 6 | Very Likely |  |  | 6 Very Likely
|  | 5 | Likely |  |  | 5 Likely
|  | 4 | Possible |  |  | 4 Possible
|  | 3 | Unlikely |  |  | 3 Unlikely
|  | 2 | Highly Unlikely |  |  | 2 Highly Unlikely
|  | 1 | Remote |  |  | 1 Remote
Consequence
|  |  |  | Slight | Minor | Moderate | Major | Massive | Catastrophic
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6
| Probability | Remote | 1 | 11 | 10 | 9 | 8 | 7 | 6
|  | Highly Unlikely | 2 | 10 | 9 | 8 | 7 | 6 | 5
|  | Unlikely | 3 | 9 | 8 | 7 | 6 | 5 | 4
|  | Possible | 4 | 8 | 7 | 6 | 5 | 4 | 3
|  | Likely | 5 | 7 | 6 | 5 | 4 | 3 | 2
|  | Highly Likely | 6 | 6 | 5 | 4 | 3 | 2 | 1
|  | Risk Category | Description
| 0 | 0 | Low
| 1e-05 | 1 | Extreme
| 0.2 | 5 | High
| 0.4 | 7 | Medium |  |  |  | Rating | Priority
| 0.6 | 9 | Low |  |  |  | Extreme | 1
[7 empty] | High | 2
[7 empty] | Low | 4
|  | Adequacy # | Adequacy |  |  |  | Medium | 3
|  | 1 | Inadequate
|  | 2 | Somewhat Inadequate
|  | 3 | Mostly Adequate
|  | 4 | Appropriate
|  | 5 | Exceeds Req'ts
Source: Security Risk Management Aide-Mémoire
www.srmam.com
What is the likelihood of this type of consequence occurring in the next twelve months for the Group.
Note on C12: Insert number based on the on the consequence.
Note on C20: Insert number based on probability.